## AnnualWorkPlan2020-2021
Goal | Objective | Action Description | Lead Contact | Second Contact | Year | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Proposed Deadline | Completed? Y/N | Notes: | Funding Source(s) | Funding Description | Budget Category | Budget Subcategory
A. Increase RCD capacity (Long-term Goals 1,2,6) | A-1. Conduct planning | Identify program and grant opportunities for 2021 and 2022 | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Focus on opportunities that address long-term goals. | YWPFSC | Staff time billed to YWPFSC | Capacity Building | Identifying Funding Opportunities
|  | Share and discuss opportunities with other Board members and identify members to develop program/grant concepts | Board |  | 20 & 21 | [18 empty] | Scheduled RCD Meetings |  | Identify funding sources (see below) while developing projects and programs that fulfill the YCRCD Long Range Plan. |  |  | Capacity Building
|  | Draft, revise and approve 2021 Budget & Work Plan | Board | Jeanene | 20 & 21 | [18 empty] | Jan 2021 RCD Mtg, Jan 2022 RCD Mtg |  | Subtask A: Identify community needs, and program and grant opportunities; Subtask B: Review potential projects with partners, potential funders; Subtask C: Draft work plan and budget; incorporate collaborative partner activities, fundraising activities | DOC_RCD_FAP (Task 1); YWPFSC | DOC Task #1: Staff time $985.60, match $246.40. YWPFSC billed for staff time | State Requirements | Budget & Workplan | bar: Nov to Jan; Nov to Dec
| A-2. Perform administrative tasks | Respond to public enquires, track finances, maintain office space | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Assist with acquisition of computer equipment, software, office supplies; assist with tracking grant expenditures and payroll; assist with response to public enquires | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Overhead
|  | Draft and post agenda, compile meeting notes, post meeting notes on website | Alyssa, Deborah | Jeanene | 20 & 21 | [18 empty] | 1-week prior through 1-week after RCD meeting |  |  | YWPFSC | Staff time billed to YWPFSC | State Requirements | Public Transparency Requirements
|  | Complete annual audit | Board | Auditor | 21 | [18 empty] | Complete by July 2021 |  | Yuba County will provide recommendations for auditor | YWPFSC, DOC_RCD_FAP | YWPFSC allocation $2500. DOC allocation $600, match is $150 | State Requirements | Annual Audit | bar: Apr to Jun
|  | Acquire insurance | Board | Deborah | 21 | [18 empty] | Complete by Jan 2021 |  |  | YWPFSC, DOC_RCD_FAP | YWPFSC allocation $6000 to cover three years. DOC allocation $2400, match is $600 | bar: Jan
|  | Draft, revise, and approve annual report | Board | Jeanene | 20 & 21 | [18 empty] | Mar 2021 RCD mtg |  |  | DOC_RCD_FAP (Task 2); YWPFSC | DOC Task #2: Staff time $98.56, match is $24.64. YWPFSC billed for staff time | State Requirements | Annual Reports | bar: Dec to Feb; Dec
| A-3. Pursue funding | Develop fundraising strategy | Board | Jeanene | 21 | [18 empty] | Dec 2021 RCD mtg |  | Strive to identify diverse funding options. Subtask A: Identify ways that RCDs and similar organizations raise funds; Subtask B: Identify a subset that are viable for YCRCD and develop a strategy for pursuing these options | DOC_RCD_FAP (Task 4); YWPFSC | DOC Task #4: Staff time $492.80, match is $123.20. YWPFSC billed for staff time | Capacity Building | Identifying Funding Opportunities | bar: Jan to Dec
|  | Seek support from Yuba County Board of Supervisors and Yuba Water Agency to fund part-time staff member | Board |  | 20 | [18 empty] | June 2020 | Yes | Yuba Water Agency provided funding to YWPFSC which then provided $15,900 for basic operating expenses in 2020-21; staff time costs will be covered separately |  |  | Capacity Building | Identifying Funding Opportunities | bar: Jul to Oct
|  | Develop grant application and apply for RCD capacity-building grant | Board | Jeanene | 20 | [18 empty] | June 25, 2020 | Yes | Received approval for total of $15,068; match requirement is $3,767. |  |  | Capacity Building | Grant Application | bar: Jul; Oct
|  | Identify funding sources for programs including fees for service-related projects | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | To also include running advertisement with Yuba-Sutter Farm Bureau to let farmers know about the NRCS programs available to them. | YWPFSC | Staff time billed to YWPFSC | Capacity Building | Identifying Funding Opportunities
|  | Develop and submit grant applications to funding sources identified above | Board | Jeanene | 20 & 21 | [18 empty] | Submit applications when ready |  | Work with Yuba Water Agency grant writer to apply for project and capacity building grants. As Board members and staff become more knowledgeable about grant writing through training, need to rely on outside assistance will decrease. | DOC_RCD_FAP (Task 3); YWPFSC | DOC Task #3: Staff time $492.80, match is $123.20. YWPFSC billed for staff time | Capacity Building | Grant Application
| A-4. Develop partnerships | Develop partnerships with groups involved in watershed and forest health | Board | Jeanene | 20 & 21 | [18 empty] | Add collaborative projects to workplan as they are developed |  | Continue to establish the role of the RCD within the context of watershed and forest health. Subtask A: Attend local agency and other organizations' meetings; Subtask B: Meet with members of local agencies and organizations to discuss and develop collaborative project ideas | DOC_RCD_FAP (Task 5); YWPFSC | DOC Task #5: Staff time $123.20, match is $30.80; travel $483.00, match is $120.75. YWPFSC billed for staff time | Administrative Costs | Partnership Building
|  | Work with NRCS to hold Yuba-Sutter Work Group | Alyssa | Jeanene | 21 | [18 empty] | Feb 2021 |  | Work with local NRCS office to schedule work group for RCD partners to meet, introduce themselves, and discuss programs and projects. | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partnership Building | bar: Dec to Feb
|  | Continue to develop partnerships with YWA and YWPFSC | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Attend regularly scheduled YWA and YWPFSC meetings, identify future program and project needs related to the health of the Yuba watershed and associated forestlands . | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partnership Building
|  | Participate in annual Foothill Community Cleanup weekend | Board | Jeanene | 21 | [18 empty] | June 2021 |  | Partner with Yuba County, Recolocy, and Camptonville Community Partnership to host annual foothill coomunity clean-up weekend; through outreach, work toward more involvement in 2022 event | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partnership Building | bar: Jan to Dec
|  | Develop collaborations with Sutter County RCD, the CA Association of Resource Conservation Districts (CARCD), and other RCDs | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Participate in scheduled calls | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partnership Building
|  | Explore potential for developing partnerships related to habitat conservation and restoration for Monarch butterflies | Alyssa, Deborah | Jeanene | 21 | [18 empty] | Ongoing |  | Participate in training, workshops, calls | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partnership Building | bar: Jan to Dec
| A-5. Encourage training for Board members and staff | Identify and support training opportunities | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Take advantage of board and staff training opportunities that arise throughout the year. Many are offered through CARCD and SNC. Includes software training, grant writing classes, and opportunities to expand knowledge on natural resource management. | DOC_RCD_FAP (Task 6); YWPFSC | DOC Task #6: DOC staff time $295.68, match is $73.92; DOC training allocation $1200, match is $300; DOC travel $1123, match is $280.75. YWPFSC travel $2000 over two year period; YWPSC billed for staff time | Administrative Costs | Training
|  | Attend CARCD Annual Conference | Board member | Staff member | 20 & 21 | [18 empty] | Nov 2020, fall 2021 | ? | California Association of Resource Conservation Districts. Location TBD. One Board member and one staff member to attend CARCD Annual Conference. | As above | As above | Administrative Costs | Meetings/Travel | bar: Nov; Oct
|  | Attend Sacramento Valley Region RCD meetings | Board |  | 20 & 21 | [18 empty] | Oct 2020, spring and fall 2021 | Board attended Oct 2020 mtg |  | As above | As above | bar: Oct; Mar; Oct
|  | Attend other county or state RCD meetings, workshops and seminars on resource management and related topics | Board | Jeanene | 20 & 21 | [18 empty] | Ongoing |  |  | As above | As above | Administrative Costs | Meetings/Travel
B. Develop and participate in education and outreach activities (Long-term Goals 1,2) | B-1. Upgrade website | Contact CARCD to acquire RCD website template, move current content into new template, and update website | Deborah | Jeanene | 20 & 21 | [18 empty] | 2021-12-01 |  | Subtask A: Update website to meet state requirements (update website to meet suggested CARCD criteria, comply with state laws, and address any needed upgrades). | DOC_RCD_FAP (Task 8); YWPFSC | DOC Task #8: DOC staff time $295.68, match is $73.92. YWPFSC website $120 over two year period; YWPFSC billed for staff time | Administrative Costs | Outreach: Website
| B-2. Improve website | Locate and add resources to website | Deborah | Jeanene | 20 & 21 | [18 empty] | Ongoing |  | Subtask B: Locate and add resources to website including educational brochure (as well as new programs, maps, and any additional relevant information about the RCD). | As above | As above | Administrative Costs | Outreach: Website
| B-3. Present annual report to local agencies | Provide brief presentation to Yuba County Board of Supervisors, Yuba Water Agency and other local agencies on work accomplished by RCD in 2020 | Alyssa | Jeanene | 21 | [18 empty] | 2021-06-01 |  | Outreach to local agencies increases visibility | DOC_RCD_FAP (Task 7); YWPFSC | DOC Task #7: Staff time $739.20, match is $184.80; printing $400, match is $100; travel $483.00, match is $120.75. YWPFSC billed for staff time | Administrative Costs | Outreach: Presentation Development | bar: Mar to Jun
Meetings/Travel | bar: Mar to Jun
| B-4. Develop and distribute outreach materials | Identify gaps in available materials on fostering healthy watersheds and forests and develop needed outreach materials; develop program materials to provide to the local communities | Board | Jeanene | 21 | [18 empty] | Ongoing |  |  | As above | As above | Administrative Costs | Outreach: Pamphlet Development | bar: Jan to Dec
C. Develop and implement programs (Long-term Goals 1,3) | C-1. CalRecycle Grant | Collect Landowner Info for CalRecycle Grant | Alyssa | Jeanene | 20 & 21 | [18 empty] | July, 2020; July 2021 | 2020 -Yes | For Farm and Ranch cleanup - Participate in grant program to assist landowners with solid waste cleanup in order to abate a nuisance, public health, safety threat and/or a threat to the environment | DOC_RCD_FAP (Task 9); CalRecycle Grant; YWPFSC | DOC Task #9: Staff time $197.12, match is $49.28. CalRecycle: admin costs $7,839. YWPFSC billed for staff time | Special Projects | CalRecycle Grant | bar: Jul; Jul
|  | Apply for CalRecycle Grant | Alyssa | Jeanene | 20 & 21 | [18 empty] | Aug 2020; Aug 2021 | 2020 -Yes |  | As above | As above | bar: Jul to Aug; Jul to Aug
|  | Implement CalRecycle Grant | Alyssa | Jeanene | 20 & 21 | [18 empty] | June 2021 |  | For 2021 application, dependent on whether receive grant | As above | As above | bar: Sep to Jun; Sep to Dec
| C-2. AB38 Fee-for-Service Program | Develop outline of AB38 Fee-for-Service Program | Gary | Alyssa | 20 & 21 | [20 empty] | DOC Subtasks A-G. Assembly Bill 38 was signed into law by the Governor on October 2, 2019 and will establish a first ever statewide fire retrofit program. When a property is in a high or very high fire hazard severity zone, a Seller must provide the Buyer with required documentation on how to harden a home against fire, compliance with defensible space laws, compliance with state and/or local vegetation management ordinances, and a list of low-cost retrofits to harden a home against fire. By working with the Yuba Sutter Realtors Association and home Sellers, this program will help home Sellers meet state and local requirements. Will establish a fee-for -service program. | DOC_RCD_FAP (Task 10); YWPFSC | DOC Task #10: Staff time $2069.76, match is $517.44; printing $800, match is $200; travel $483.00, match is $120.75. YWPFSC billed for staff time |  | AB38 | bar: Jul to Feb
|  | Meet with realtors and other partners to discuss AB38 Fee-for-Service Program | Gary | Alyssa | 20 & 21 | [20 empty] | Work with Yuba Sutter Realtors Association, Liz Skutley, Board President, to obtain feedback and create partnerhship for the new program. Other possible partners may include local realtors and fire safe council. | As above | As above | bar: Nov to Apr
|  | Develop draft document of AB38 Program along with draft fee schedule and forms | Gary | Jeanene | 21 | [21 empty] | As above | As above | bar: Feb to May
|  | Meet with realtors and other partners to discuss draft document, fee schedule and forms for AB38 Program | Gary |  | 21 | [21 empty] | As above | As above | bar: Feb to May
|  | Develop draft outreach material and contact process for AB38 Program | Gary | Jeanene | 21 | [21 empty] | As above | As above | bar: Feb to May
|  | Develop and provide presentation for Yuba Sutter Realtors Association, other interested entities | Gary | Jeanene | 21 | [21 empty] | As above | As above | bar: May to Jun
|  | Develop MOUs as needed | Gary, Alyssa | Jeanene | 21 | [21 empty] | As above | As above | bar: Jun to Dec
|  | Finalize program documents, fee schedule and forms,and print outreach materials | Gary | Jeanene | 21 | [21 empty] | As above | As above | bar: Jun
|  | Implement and manage Final AB38 Program including outreach to community | Gary | Jeanene | 21 | [18 empty] | Implement July 2021 |  |  | As above | As above | bar: Jul to Dec
| C-3. Foothill Cleanup Program | Develop draft of Foothill Cleanup Program | Gary & Alyssa | Deborah | 20 & 21 | [20 empty] | Discuss proposed program with Yuba Water Agency. Work with Yuba Watershed Protection and Fire Safe Council and Camptonville Community Partnership to identify properties owned by low-income or disababled individuals in need of waste removal in the vicinity of their homes. Removal of waste increases wildfire safety, reduces materials hazardous to watershed health, and reduces potential hazards for firefighters and the local community during a fire. Identify potential contractors and determine potential costs associated with cleanup and removal of waste. Develop program goals and narrative. | DOC_RCD_FAP (Task 11); YWPFSC | DOC Task #11: Staff time $985.60, match is $246.40; printing $320, match is $80. YWPFSC billed for staff time. |  | Foothill Cleanup | bar: Oct to Mar
|  | Develop presentation for Yuba Water Agency on Foothill Cleanup Program | Gary & Alyssa | Jeanene | 21 | [21 empty] | As above | As above | bar: Feb to Mar
|  | Finalize Foothill Cleanup Program documents and apply for Yuba Water Agency Grant for Foothill Cleanup Program | Gary & Alyssa | Jeanene | 21 | [20 empty] | Strive to write this grant using YCRCD resources | As above | As above | bar: Feb to Mar
|  | Identify other sources of grant funding for this work and pursue | Gary & Alyssa | Jeanene | 21 | [21 empty] | As above | As above | bar: Feb to Dec
|  | Develop outreach material for Foothill Cleanup Program | Gary & Alyssa | Jeanene | 21 | [20 empty] | Create flyer and landowner forms. Hire contractor(s). | As above | As above | bar: Feb to Dec
|  | Implement and manage Foothill Cleanup Program | Gary & Alyssa | Jeanene | 21 | [18 empty] | September 2021 |  | Work with identified landowners and contractor to complete property cleanup. | YWPFSC | Staff time billed to YWPFSC | bar: Sep to Dec
| C-4. Yuba-Sutter Specialty Crop Technical Assistance Hub Program | Assist Sutter RCD with implementation and management of technical assistance hub program | Alyssa | Jeanene | 20 & 21 | [18 empty] | Spring 2021 |  | Work with Sutter County RCD staff. Staff time will include training, host grower relations, grower outreach and advertising, content creation, event coordination, pre/post event surveys, grower follow-up, online resource library maintenance. | Y-S SCTAH | Staff time $7500; some staff mileage $ provided; 5.33% admin overhead on staff time ($399.75) |  | Y-S Technical Assistance Hub
D. Support partner activities (Long-term Goals 1,4,5) | D-1. Support programs that build fire resilience and forest health | Support Camptonville Community Partnership biomass facility and associated biomass utilization projects | Board |  | 20 & 21 | [18 empty] | Ongoing |  |  | YWPFSC | Staff time billed to YWPFSC | Administrative Costs | Partner Support
|  | Collaborate with YWPFSC on firesafe-related activities | Gary | Deborah | 20 & 21 | [18 empty] | Ongoing |  |  | YWPFSC | Staff time billed to YWPFSC